## Sheet1
Timeline Pengerjaan
No | Pengerjaan | Juni | [8 empty] | Juli | [30 empty] | Agustus
|  | R | K | J | S | M | S | S | R | K | J | S | M | S | S | R | K | J | S | M | S | S | R | K | J | S | M | S | S | R | K | J | S | M | S | S | R | K | J | S | M | S | S | R | K | J | S | M | S | S | R | K | J | S | M | S | S | R | K | J | S | M
|  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Database : Skema Relasional | bar: Juli J 1; Juli S 4
2 | Skeleton Web : Model, View | bar: Juli S 4 to Juli J 8
3 | Model alumni, user, friend_relationship, education, gender, friend_request, unit | bar: Juli S 5 to Juli R 6
4 | Model category_event, event, host_event, interest, interested_in, visibility_status, rsvp_event, work_experience | bar: Juli R 6 to Juli K 7
5 | Model testing, penyempurnaan | bar: Juli K 7 to Juli J 8; Juli S 11 to Juli J 15
6 | View about_us, contact, history, home_view, link_web, sign_in_view, sign_up_view, visimisi | bar: Juli S 4; Juli K 7 to Juli J 8; Juli S 11
7 | View my_profile_view, show_profile_view, host_event_view, find_friend_view | bar: Juli S 5; Juli S 12 to Juli K 14
8 | edit_profile_view, edit_profile_location_view, edit_profile_education_view, edit_profile_work_view, edit_profile_visibility_view | bar: Juli R 6; Juli S 18 to Juli R 20
9 | View my_calendar_view, main_event_view, show_event_view | bar: Juli K 21
10 | Controller | bar: Juli S 4 to Juli J 8; Juli S 11 to Juli J 15; Juli S 18 to Juli J 22; Juli S 25
Keterangan :
1. Iterasi I berupa skeleton Fitur
2. Iterasi II, III berupa penyempurnan serta perbaikan fitur